[](https://sportsfieldsolutionsllc.com/)

Scott A. Bills, CSFM

Certified Sports Field Consultant

SPORTS FIELD SOLUTIONS, LLC

PO Box 131, Baptistown, NJ 08803

908-268-8866

[sportsfieldsolutions31@yahoo.com](mailto:sportsfieldsolutions31@yahoo.com)

[www.sportsfieldsolutionsllc.com](http://www.sportsfieldsolutionsllc.com)

PROJECT EVERGREEN/STMA VOLUNTEER FIELD PROJECT

Mother Mathilda Beasley Park – Skinned Ballfield

500 East Broad Street

Savannah, GA 31401

**SCOPE OF WORK**

Demolition

1. Remove existing wooden landscape timber wall.
   1. Option 1 – Remove 130 linear feet of timber wall from the steps along the right field line to the telephone pole behind the backstop.
   2. Option 2 – Remove the entire timber wall, approximately 250 linear feet.

Note: The timbers, nails and rebar removed will be stockpiled or loaded onto Chatham County trucks for disposal by the county.

Wall Construction

1. Supply and install pre-cast modular wall units or 6”x6”x8’ pressure treated timers to construct a new retaining wall on a 4-6 inch stone base. The wall to be a finished height of 21-24 inches. Backfill the wall with ¾” clean stone.

Option 1 – **Pre-Cast Modular Wall Units** - Construct a 130 linear foot wall (260 Square Face Feet

of Wall Units and 130 Linear Feet of Caps)

15 Tons of ¾” clean stone will be needed for the base and back of the wall.

500 Square Feet of a non-woven Geotextile Filter Fabric.

12 Large Tubes of construction adhesive will be needed to glue the caps.

**6”x6”x8’ Pressure Treated Timbers** – 64 Timbers, 32 - 1/2” x 24” Re-bar, 96 - 8”

Heavy Duty nails/spikes

1. Tons of ¾” clean stone will be needed for the base and back of the wall.

500 Square Feet of a non-woven Geotextile Filter Fabric.

Option 2 – **Pre-Cast Modular Wall Units** - Construct a 250 linear foot wall (500 Square Face Feet

of wall and 250’ of cap stone)

30 Tons of ¾” clean stone will be needed for the base and back of wall.

1,000 Square Feet of a non-woven Geotextile Filter Fabric.

24 Large Tubes of construction adhesive will be needed to glue the caps.

**6”x6”x8’ Pressure Treated Timbers** – 128 Timbers, 64 - 1/2” x 24” Re-bar, 192 - 8”

Heavy Duty nails/spikes

1. Tons of ¾” clean stone will be needed for the base and back of the wall.

1,000 Square Feet of a non-woven Geotextile Filter Fabric.

Infield Work

1. Survey the infield to determine existing and proposed grades of the infield, home plate, pitching rubber and

Bases.

1. Layout the infield radius to a distance of 65 feet from the pitching rubber.
2. With a sod cutter remove all grass within the new radius and existing infield mix and remove all soil to a depth of 3-4 inches.
3. Move all of the excavated grass and soil to the void created from removing the timber wall, grade and seed.
4. Remove all remaining weeds and build up of infield mix from the front of the backstop, player benches and remainder of the infield. Move all debris to a location designated by the County.
5. Layout the proper elevation, distance and orientation of Home Plate. Supply and install a new 3” all rubber Home Plate.
6. Layout the batter’s boxes (3’x6’) and catcher’s/umpire’s box (4’x4). Remove all existing infield mix to a depth of 3-4 inches and move to low areas of the infield or voids created from removing grass.
7. Supply and install bagged Mound Clay (40 – 50# Bags) and compact in 1-2 inch lift with a motorized vibratory plate compactor and hand tamp.
8. Layout the proper elevation, distance and orientation of the Pitching Rubber. Supply and install a new 4-Way Pitching Rubber.
9. Layout the pitching area (3’x8’). Remove all existing infield mix to a depth of 3-4 inches and move to low areas of the infield or voids created from removing grass.
10. Supply and install bagged Mound Clay (40 – 50# Bags) and compact in 1-2 inch lift with a motorized vibratory plate compactor and hand tamp.
11. Grade the existing infield to cut high areas and fill low areas.
12. Supply and install 50 Tons of the same infield mix already used on the infield. Supplier to be provided by the County.
13. Grade the infield to meet the grass edges and ensure efficient surface drainage.
14. Supply and topdress the infield with 40 Bags of infield condition
15. Groom ready for play.

Additional Work

1. Grade and seed all disturbed areas in front and behind the newly constructed wall.
2. Powerwash the aluminum player benches, bleachers and concrete pad.
3. Fence – Option 1 – Replace all mesh on the fencing along the base paths and backstop.

Option 2 - Repair the existing chain-link fence mesh to ensure sharp tines are not facing the

playing surface, install new aluminum ties to re-anchor any lose areas of fence,

especially at the bottom and straight all damaged where possible.

Paint the fence with a black or silver paint.

**MATERIALS**

Wall Construction

Option 1 – **Pre-Cast Modular Wall Units** - Construct a 130 linear foot wall (260 Square Face Feet

of Wall Units and 130 Linear Feet of Caps)

15 Tons of ¾” clean stone will be needed for the base and back of the wall.

500 Square Feet of a non-woven Geotextile Filter Fabric.

12 Large Tubes of construction adhesive will be needed to glue the caps.

**6”x6”x8’ Pressure Treated Timbers**

64 Timbers

32 - 1/2” x 24” Re-bar

1. - 8” Heavy Duty nails/spikes

16 Tons of ¾” clean stone will be needed for the base and back of the wall.

500 Square Feet of a non-woven Geotextile Filter Fabric.

Option 1 – **Pre-Cast Modular Wall Units** - Construct a 260 linear foot wall (500 Square Face Feet

of Wall Units and 130 Linear Feet of Caps)

30 Tons of ¾” clean stone will be needed for the base and back of the wall.

1,000 Square Feet of a non-woven Geotextile Filter Fabric.

24 Large Tubes of construction adhesive will be needed to glue the caps.

**6”x6”x8’ Pressure Treated Timbers**

128 Timbers

1. - 1/2” x 24” Re-bar

192 - 8” Heavy Duty nails/spikes

32 Tons of ¾” clean stone will be needed for the base and back of the wall.

1,000 Square Feet of a non-woven Geotextile Filter Fabric.

Infield Work

50 Tons of local Infield Mix (Source to be provided by the County)

80 Bags of Bagged Moisturized Mound Clay (Turface, Marco, DuraPitch, etc)

40 Bags of Infield Conditioner (Turface, Pro’s Choice, DuraEdge, Diamond Pro, etc)

New Base Set with Double 1st Base with male posts, female anchors and Plugs

New 24” 4 Way Home Plate

New 3” Official All Rubber Home Plate with Solid Wood Bottom

Additional Work

100 lbs of a Triplex Perennial Ryegrass Seed mix or Fescue/Perennial Ryegrass mix.

50 lbs of a 10-20-10 or similar starter fertilizer

10 Bags of Penn Mulch or 5 Bales of Straw/Salt Hay

100 – 8” 9 Gauge Chain Link Fence Ties (Home Depot - $16.00)

2 – 1 Gallons of Rust-Oleum Metallic Chain Link Fence Paint (Home Depot - $70.00 for a 2 Gallon Pack)

Paint Brushes or Rollers, Pans, Plastic Tarp (Home Depot - $100.00)

**CONTRACTORS, TOOLS AND EQUIPMENT**

Wall Demolition and Construction

* 1 -Small (25-35 HP) Tractor with a front bucket and/or forks and operator
* 2 – Wheel Barrows
* 2 - Pick Axes
* 2 – Full Size Sledge Hammers
* 2 – Smaller Hand Mauls
* 1 – Chain Saw with a minimum 16” bar
* 1 – Cut Off Saw with a 12’ Diamond Blade
* 1 – Rotary Drill
* 2 – ½” Long Wood Bits
* 2 – 3/8” Long Wood Bits
* 2 – Long Handled Flat Shovels
* 2 – Long Handled Flat Spades
* 2 – Long Handled Pointed Shovels
* 2 – Long Handled Steel Rakes
* 2 – 4’ levels
* 2 – 8”x8” Hand Tamps
* Misc – 2 Measure Tapes, Marker/Pencil, Extension Cords, Utility Knife(s)etc
* 8-10 Volunteers and one Equipment Operator

Infield Work

* Laser Level – Scott will rent at Home Depot or local supplier
* 1 – Small (25-35 HP) Tractor with Turf Tires and a front bucket or Skid Steer w/Tracks and a front bucket.
* 1 - Power Edger
* 1 - Sod Cutter
* 2-3 50 lb.Broadcast Spreaders
* 1 -Motorized Vibratory Plate Compactor
* 1 - Infield Grader/Groomer – ABI Force/Toro/John Deere/Smithco?
* Hand Tools – 4-6 Flat Shovels, 4-6 Infield Rakes, 2-3 Stiff Brooms, 2-3 Hand Tamps, 1-2 Backpack Blowers,
* 3-4 Wheel Barrows
* 10-12 Volunteers, one infield grader operator and one tractor operator

Additional Work

* 1 - Power Washer and Hose
* Paint Brushes and/or Rollers, Pans, Wire Brushes, Tarps
* 1-2 Ladders (6’-12’ step and/or extension ladders)
* Misc – Pliers, Wire Cutters, Utility Knifes, Rags, Gloves,
* 4-6 Volunteers